# Sample Special Events Timeline

Concerts and Performances

Week 12 (or earlier):

- Select and confirm artists.  Use personal contacts if at all possible.  Send a letter describing the event and its purpose, the organization’s work and its goals, and others who are involved or who have been involved in the past.

- Confirm details with artist’s manager and/or publicist

- Review contract(s) with appropriate (pro bono if you’re lucky) attorney

- Identify and confirm volunteer co-chairs

- Select a date.  The artist’s availability will be a major factor.  Other major considerations include the venue’s availability, competing events, day of the week, and appropriateness of the season.

- Select and confirm the venue.  Factors to consider include:  Location suited to the artist’s following, union or non-union (Affects costs), parking and public transportation, public safety, and accessibility to persons with disabilities.

- Hire technical crew and security

- Arrange insurance

- Make travel arrangements for artist(s)

- Hire/recruit publicity and promotion staff

- Apply for any needed city permits (for such things as closing off a street corner, re-directing traffic, renting portable toilets, portable booths, food concessions, liquor sales, and unusual visual and sound effects—such as fireworks!)

Weeks 10-11

- Publicity and promotion begins:  Organize/develop press list, check on listing deadlines, select poster design

- Choose method of ticket sales:  Contract with ticket service or handle within your organization; contract with web sales service (unless your organization already sells things on line)

- Co-chairs help with lists of contacts:  invitees, donors of services, press and volunteers

- Hire technical staff, including stage and house managers, sound and light designers, dee jays, etc.

- Obtain hall/theater specifications from venue and stage/technical needs from artist

- Work with technical crew to select needed technical equipment.  If not available within venue, contract sound and lighting (and fireworks) companies.

- Recruit and organize volunteers by skills and availability.

- Design and prepare promotional materials such as buttons, tee shirts, and hats.

- Recruit and brief a knowledgeable speaker (maybe your board chair?) to speak at the event.

# Weeks 8-9

- Print and distribute poster and flyers

- Begin ticket sales

- Distribute press releases

- Write and distribute public service announcements to radio and TV stations

- Plan a press conference (if you have a compelling idea that would attract attention) or smaller-scale promotion like ticket give-aways on the radio

- Estimate needed security staff and hire security

- Compare artists’ stage plots to hall specifications and double-check about any additional needed equipment

- Plan event volunteer needs

Weeks 5-7

- Assess volunteers’ skills and assign them to committees/tasks

- Plan and secure needed materials for information tables, booths, and concessions

- Make follow-up calls to the press

- Schedule production crew meeting

Weeks 3-4

- Produce press conference or other press promotion

- Develop time schedule for the event

- Meet with technical crews, house managers, master of ceremonies, and other key staff to review and refine time schedule

- If you expect a large crowd, contract with and confirm medical staff (generally one doctor and assistant)

- Arrange food for event staff day-of-show

- Arrange food and beverages for artists’ dressing rooms

- Arrange comp tickets and artists’ passes for guests and press

Weeks 1-2

- Make follow-up calls to previously mailed press releases

- Coordinate radio and TV interviews

- Prepare press packets

- Hold final “walk through” with technical staff and security chief

- Prepare for sales of tee shirts, buttons, and other merchandise

- Organize backstage passes

- Confirm all volunteers and their roles

- Confirm artists’ travel and accommodations

Day before show

- Compile event necessities, including:

- Cash boxes with change in appropriate denominations

- Receipts

- Credit card equipment and receipts

- Literature about your organization

- Merchandise you will sell

- Sign-up lists and guest lists

- Backstage pass lists

- Ice chests and bottled water

- Name tags for committee members and volunteers

- Emergency numbers for police, fire, security, and medical staff

- All contact phone numbers (performers’ hotel, hosts, speakers, suppliers)

- Emergency cash

- Posterboard

- Pens and markers for signs

- First aid kit

- Microphones and sound system (if facility does not have them)

Day of show

- Pick up artists’ at the airport

- Send artists flowers/candy/other complimentary items

- Greet press and distribute press packets

- Coordinate complimentary tickets and guest passes

- Distribute backstage passes

- Check with stage manager and house manager to keep event on schedule

- Check with event security staff

- Set up and monitor sales of concessions

- Arrange meals for staff and artists

- Clean up

- Count your proceeds!

Post-show

- Thank and recognize artists, volunteers, and crew

- Hold a follow-up meeting with organizers to discuss what worked and what didn’t work

- Prepare notes for your files and/or the next event coordinators